## Requirements List
Requirements List
|  | Simple | Average | Complex |  | Sum Range | Difficulty Range
| EI. External Input | 1 | 3000 | 0 |  | C$11:C$400 | D$11:D$400
| EO. External Output | 1004 | 2 | 2 |  | E$11:E$400 | F$11:F$400
| EQ. External Inquiry | 0 | 0 | 0 |  | G$11:G$400 | H$11:H$400
| ILF. Internal Logical File | 1000 | 0 | 0 |  | I$11:I$400 | J$11:J$400
| EIF. External Interface File | 1 | 202 | 0 |  | K$11:K$400 | L$11:L$400
|  | EI |  | EO |  | EQ |  | ILF |  | EIF
ID | Requirement | Number | Difficulty | Number | Difficulty | Number | Difficulty | Number | Difficulty | Number | Difficulty
REQ001 | SW data image elaboration |  |  | 2 | Complex |  |  | 1000 | Simple
REQ002 | ML (filtering data) | 3000 | Average | 1000 | Simple |  |  |  |  | 1 | Simple
REQ003 | Testing |  |  | 2 | Average
REQ004 | User interactions (NASA) | 1 | Simple | 1 | Simple
REQ005 | Vulnerability assessment HW |  |  | 1 | Simple |  |  |  |  | 200 | Average
REQ006 | Vulnerability assessment SW |  |  | 2 | Simple |  |  |  |  | 2 | Average
Use this sheet to associate requirements to elements of the FP assessment. For each relevant requirement list how many EI, EO, EQ, EIF, or ILF it contributes to, together with their complexity. The recap table provides the data which can then be pasted in the FP assessment sheet (see Function Points sheet).
For details about the computation, have a look at “Introduction to Software Project Management”, by CRC Press (http://www.spmbook.com)
External Inputs (User Inputs): Screens, forms, dialog boxes, and other messages with which an end-user or another application adds, deletes, or changes the applications’ data.
External Outputs (User Outputs): Screens, reports, graphs, or messages the application generates for use by an end-user or another application. Outputs can process, combine, and/or summarize complex data and can also be highly formatted.
External Inquiries: Input/output combinations through which input values result in a immediate, simple output. Inquiries result in a direct search of the database for specific data, which is then used as a key to create the simple output. Inquiries retrieve data directly form the database and provide only the most rudimentary formatting.
Internal Logical Files: Major logical groups of end-user data or control information that are completely controlled by the application. A logical file can be a single flat file or a single table in a relational database.
External Interface Files: Files controlled by other applications with which this application must interact. External interface files include each major logical group of data or control information that enters or leaves the application
Simple approach (imprecise): expert judgement.
Structured approach: decompose each element into more elementary components (DET and FTR) and use the complexity tables in the next sheet.
This is version: 1.0 - released 2015.05
(C) 2015 Adolfo Villafiorita
License: MIT (http://opensource.org/licenses/MIT)
(but if you attribute the work, I appreciate)
For details about the computation, have a look at “Introduction to Software Project Management”, by CRC Press (http://www.spmbook.com)
1. User inputs: the number of user inputs, or elements in the system which require an input from the user. 2. User outputs: the number of user outputs, or elements in the system which produce an output. 3. User inquiries: the number of user inputs that generate a software response, such as word count, search result, or software status. 4. Internal logical files: the number of files created and used dynamically by the system. 5. External interfaces: the number of external files that connect with the software to an external system. For instance, if the software communicates with a device, it is counted as one external interface.

## Function Points
System Evaluation Recap
| Input Data |  |  | Weights
| Simple | Average | Complex | Simple | Average | Complex | Total
EI. External Input | 1 | 3000 | 0 | 3 | 4 | 6 | 12003
EO. External Output | 1004 | 2 | 2 | 4 | 5 | 7 | 4040
EQ. External Inquiry | 0 | 0 | 0 | 3 | 4 | 6 | 0
ILF. Internal Logical File | 1000 | 0 | 0 | 7 | 10 | 15 | 7000
EIF. External Interface File | 1 | 202 | 0 | 5 | 7 | 10 | 1419
Unadjusted Function Points | [6 empty] | 24462
Correcting Factors | [6 empty] | Value
0 = None; 1 = Low; 2 = Little; 3 = Average; 4 = High; 5 = Very High
Does the system require reliable backup and recovery? | [6 empty] | 4
Are data communications required? | [6 empty] | 5
Are there distributed processing functions? | [6 empty] | 5
Is performance critical? | [6 empty] | 2
Will the system run in an existing, heavily utilized operational environment? | [6 empty] | 2
Does the system require on-line data entry? | [6 empty] | 0
Does the on-line data entry require the input transaction to be built over multiple screens or operations? | [6 empty] | 0
Are the master files updated on-line? | [6 empty] | 0
Are the inputs, outputs, files or inquiries complex? | [6 empty] | 5
Is the internal processing complex? | [6 empty] | 5
Is the code to be designed reusable? | [6 empty] | 1
Are conversion and installation included in the design? | [6 empty] | 2
Is the system designed for multiple installations in different organizations? | [6 empty] | 0 | Complexity Tables
Is the application designed to facilitate change and ease of use by the user? | [6 empty] | 1 | They determine how to rank a particular input/output (EI, EO, EQ, ILF, EIF)
Value Adjustment Factors | [6 empty] | 0.97
[8 empty] | EI | DET
Function Points | [6 empty] | 23728.14 | FTR | 1..4 | 5..15 | > 15 | DET = Data Element Types (field)
[8 empty] | 0..1 | Low | Low | Average | FTP = File Type Referenced
[8 empty] | 2 | Low | Average | High | RET = Record Element Types (records)
[8 empty] | > 2 | Average | High | High
[8 empty] | EO/EQ | DET
[8 empty] | FTR | 1..5 | 6..19 | > 19
[8 empty] | 0..1 | Low | Low | Average
[8 empty] | 2..3 | Low | Average | High
[8 empty] | >3 | Average | High | High
[8 empty] | ILF/EIF | DET
[8 empty] | RET | 1..19 | 20..50 | > 50
[8 empty] | 0..1 | Low | Low | Average
[8 empty] | 2..5 | Low | Average | High
[8 empty] | >5 | Average | High | High
Use the tables in this sheet to compute the function points of a system/module. Assess the number of EI, EO, EQ, ILF, EIF and then assess the “Correcting Factors”. The Function Points can then be transformed into effort using the “Productivity Measures” equivalence tables. The Unadjusted Function Points can be transformed into lines of code using the “FP to LOC” measures. As with any other system, garbage in means garbage out .. the output cannot be better than the input data you provide! After listing the requirements (previous sheet), fill the parts in yellow.
For more details about the computation, have a look at “Introduction to Software Project Management”, by CRC Press (http://www.spmbook.com)
External Inputs (User Inputs): Screens, forms, dialog boxes, and other messages with which an end-user or another application adds, deletes, or changes the applications’ data.
External Outputs (User Outputs): Screens, reports, graphs, or messages the application generates for use by an end-user or another application. Outputs can process, combine, and/or summarize complex data and can also be highly formatted.
External Inquiries: Input/output combinations through which input values result in a immediate, simple output. Inquiries result in a direct search of the database for specific data, which is then used as a key to create the simple output. Inquiries retrieve data directly form the database and provide only the most rudimentary formatting.
Internal Logical Files: Major logical groups of end-user data or control information that are completely controlled by the application. A logical file can be a single flat file or a single table in a relational database.
External Interface Files: Files controlled by other applications with which this application must interact. External interface files include each major logical group of data or control information that enters or leaves the application
Simple approach to determining the complexity of each element: expert judgment (imprecise).
Structured approach: decompose each element into more elementary components (DET and FTR) and use the complexity tables below.
Correcting Factors. Assess the impact of each value to adjust the UFP and come out with the FP for your system. Each answer is a value between 0 (no influence) to 5 (very high impact).

## Productivity Measures
Productivity Measures
Project Type | Max FP | Base Productivity (*)
Small | 50-350 | 18
Smallish | 350-650 | 16
Middle | 650-1100 | 14
Largish | 1100-2000 | 12
Large | > 2000 | 10
(*) FP/Person-Month (21 days per month), RUP, Java (CSI PIemonte)
Source: http://www.dpo.it/smef2008/papers/SMEF08_proc_203_LANZA.pdf
Project Size in FPs | Team Size | Achievable Productivity Rates (FP/staff month) | Productivity (FP/person month) | Schedule (months)
100 | 2 | 90 | 45 | 1
300 | 3 | 40 | 13 | 2.5
600 | 4 | 30 | 8 | 5
>1200 | 8 | 25 | 3 | 6-8
Source: http://www.ksinc.com/itpmcptools/EstimatingGuidelines.pdf
Use the following table to transform Function Points into effort. Here you will find some example data (retrieved from the sources mentioned on the foot of the table).

## FP to LOC
FP to LOC Conversion
Language | Avg | Median | Low | High
C++ | 50 | 53 | 25 | 80 | 0.8
SQL | 21 | 13 | 13 | 37 | 0.01
Python | 24 | Not Specified | Not Specified | Not Specified | 0.19
Source: http://www.qsm.com/resources/function-point-languages-table
https://software.imdea.org/~juanca/papers/malsource_raid16.pdf
| 44.77 | as mean of the possible language that we need to use
TOT SLOC/FP | 1062308.828 | In particular, 80% of our code will be writed in C++, the 19% made of Python and the remaining part will be written in SQL
Use the following table to determine the equivalence between Unadjusted Function Points and source lines of code. Here you will find some example data (retrieved from the site below on Sep 2, 2014).
Go to: http://www.qsm.com/resources/function-point-languages-table for more details about the conversion, updated data, and values for more languages.

## Recap
System Evaluation Recap
| Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Subsystem Name | Priority | EI Total | EO Total | EQ Total | ILF Total | EIF Total | UFP Total | VAF Total | FP Total
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
Computations stop here
Insert here the outputs of the analysis. That is, for each software component being assessed using FP, you can here report all the data used to perform the computation. Use the “Function Points” sheet to perform the computation and the “Productivity Measures” and the “FP to LOC” to trasnform FP to effort and LOCs